## ProjectManagement
Dynamic Excel Gantt Chart (Reloaded)
Project Portfolio & Summary
Last Update |  | 2017-04-23 |  | Red | 1 |  | High | Medium | Low | Total
Project Office |  | Information Services |  | Yellow | 0 | Requested | 1 | 0 | 0 | 1
Point of Contact |  | Birendra Kumar |  | Green | 2 | Approved | 0 | 0 | 0 | 0
Portfolio Projects |  | 5 Projects |  | Blue | 2 | Planning | 0 | 0 | 0 | 0
Portfolio Budget |  | 215302 |  |  |  | In Progress | 0 | 3 | 1 | 4
Portfolio Actual |  | 99750 |  |  |  | Monitor | 0 | 0 | 0 | 0
Portfolio Balance |  | -115552 |  |  |  | Total | 1 | 3 | 1 | 5
Health | Project ID | Status | Criticality | Project Title | Summary | Project Manager | Due Date | Budget | Actual | % Complete | Days Left
Red | ABC-1234-XX001 | Requested | High | Overall CMS Functionality | 1. When browsing for content in a repository, the CMS will allow the user to select how the content is sorted. 2. The CMS will provide sorting options that include the metadata items, and must include by title, created date, and modified date. | Andy Fields B. Dole | 2017-12-31 | 1000 | 700 | 100% | 171
Blue | ABC-1234-XX002 | In Progress | Medium | Content Search Function | The CMS must support the ability of users to search by language. | W. McMahan J. Smith | 2017-12-31 | 10000 | 7800 | 76% | 171
Green | ABC-1234-XX003 | In Progress | Low | CMS - Archiving | The CMS must support content contributors to be able to archive pages, in a system database, complete with its metadata attributes and its link designations. Default archive value should be “never”. | J. Smith Q. Minsey Q. Arnold | 2017-10-01 | 13000 | 16000 | 50% | 80
Green | ABC-1234-XX004 | In Progress | Medium | Editing option for Authorized Users | The CMS will allow existing HTML templates to be edited and new ones to be created by authorized users. | R. McDonnell | 2017-10-31 | 750 | 735 | 2% | 110
Blue | ABC-1234-XX005 | In Progress | Medium | Standard Navigational & Fixed Page Components | The CMS must support the creation, modification, maintenance, and registration of standard navigational and fixed page components for the creation, modification and maintenance of page templates and types. The current set includes:  Banner {with and without Search box}  Bottom Nav  LeftNav – {Multiple instances with different links; can be turned “on” or “off” depending upon page instance}  TopNav  Channels (the tab images with rollover effects)  Footer  Utilities box | P. Bishop | 2017-11-15 | 75000 | 16378 | 17% | 125 | <- Press [TAB] here to create a new record
Formulas:
Days Left = [Due Date]-TODAY()

## Options
Health | Criticality | Status
Red | High | Requested
Yellow | Medium | Approved
Green | Low | Planning
Blue |  | In Progress
Complete
On Hold
Monitor